## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | No Dependency | Soumodip Ghosh | 3- Completed
S1 | S1 | US-002 | Workflow Creation and Project Goal Document | MUST HAVE | No Dependency | Soumodip Ghosh | 3- Completed
S2 | S2 | US-003 | Static Dataset Selection and Machine Learning and Deep Learning Models Preparation | MUST HAVE | Kaggle, US-001, US-002, Google Collab | Soumodip Ghosh | 3- Completed
S3 | S3 | US-004 | Ensemble method and Majority Voting Implementation | SHOULD HAVE | Google Collab, US-003 | Soumodip Ghosh | 3- Completed
S3 | S6 | US-005 | Gen AI Explanation Integration | COULD HAVE | Google Collab, US-003 | Soumodip Ghosh | 3- Completed
S4 | S4 | US-006 | Data Pipeline Implementation (For Dynamic Dataset) | SHOULD HAVE | US-002 | Soumodip Ghosh | 3- Completed
S5 | S5 | US-007 | Back Testing Implementation and Integration with ML Output | MUST HAVE | US-002, US-003 | Soumodip Ghosh | 3- Completed
S5 | S5 | US-008 | Fine Tune ML & DL Models | SHOULD HAVE | US-003, US-007 | Soumodip Ghosh | 3- Completed
S6 | S7 | US-009 | Model Life Cycle Implementation | SHOULD HAVE | US-002, US-003 | Soumodip Ghosh | 3- Completed
S6 | S6 | US-010 | API and Dashboard Creation | MUST HAVE | US-002 | Soumodip Ghosh | 3- Completed
S7 | S7 | US-011 | API Integration | MUST HAVE | US-010 | Soumodip Ghosh | 3- Completed
S8 | S8 | US-012 | Dashboard Testing and Validation | MUST HAVE | US-011 | Soumodip Ghosh | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 202 | 33 | 26 | 29 | 31 | 32 | 23 | 17 | 4 | 2 | 2 | 3 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T1.1 | Study market fundamentals | 26-11-25 | 27-11-26 | Soumodip Ghosh | Learning | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | T1.2 | Learn indicators (RSI, MACD etc.) | 28-11-25 | 29-11-25 | Soumodip Ghosh | Learning | 3- Completed | 5 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T2.1 | Workflow creation & ML Model selection | 30-11-25 | 2025-01-12 | Soumodip Ghosh | Learning | 3- Completed | 7 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T2.2 | Document understanding | 2025-02-12 | 2025-02-12 | Soumodip Ghosh | Documentation | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-003 | T3.1 | Explore Kaggle for dataset | 2025-03-12 | 2025-04-12 | Soumodip Ghosh | Analysis | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T3.2 | Prepare the schema of the model | 2025-05-12 | 2025-06-12 | Soumodip Ghosh | coding | 3- Completed | 7 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T3.3 | Model training | 2025-07-12 | 2025-08-12 | Soumodip Ghosh | coding | 3- Completed | 7 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | T3.4 | Document workdone | 2025-09-12 | 2025-09-12 | Soumodip Ghosh | Documentation | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-004 | T4.1 | Studying about ensemble methods | 2025-10-12 | 2025-11-12 | Soumodip Ghosh | Learning | 3- Completed | 9 | 4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T4.2 | Implementation | 2025-12-12 | 14-12-25 | Soumodip Ghosh | Coding | 3- Completed | 7 | 0 | 0 | 1 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T4.3 | Document workdone | 15-12-25 | 16-12-25 | Soumodip Ghosh | Documentation | 3- Completed | 3 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-006 | T6.1 | Starting about data pipeline | 17-12-25 | 19-12-25 | Soumodip Ghosh | Learning | 3- Completed | 9 | 4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T6.2 | Implementation | 20-12-25 | 22-12-25 | Soumodip Ghosh | Coding | 3- Completed | 8 | 0 | 0 | 0 | 3 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T6.3 | Document workdone | 23-12-25 | 23-12-25 | Soumodip Ghosh | Documentation | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-007 | T7.1 | Studying about back testing | 24-12-25 | 26-12-25 | Soumodip Ghosh | Learning | 3- Completed | 10 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | T7.2 | Implementation | 27-12-25 | 29-12-25 | Soumodip Ghosh | Coding | 3- Completed | 8 | 0 | 0 | 0 | 4 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T8.1 | Fine tuning | 27-12-26 | 29-12-26 | Soumodip Ghosh | Coding | 3- Completed | 4 | 0 | 0 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T8.2 | Document workdone | 30-12-25 | 30-12-25 | Soumodip Ghosh | Documentation | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG
US-005 | T5.1 | Study about Gen AI use case | 31-12-25 | 2026-01-01 | Soumodip Ghosh | Learning | 3- Completed | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | T5.2 | Implementation | 2026-02-01 | 2026-04-01 | Soumodip Ghosh | Coding | 3- Completed | 9 | 0 | 0 | 4 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T10.1 | API and dashboard creation | 2026-02-01 | 2026-04-01 | Soumodip Ghosh | Coding | 3- Completed | 7 | 0 | 0 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T10.2 | Document workdone | 2026-05-01 | 2026-06-01 | Soumodip Ghosh | Documentation | 3- Completed | 4 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 7 BACKLOG
US-011 | T11.1 | API integration | 2026-01-07 | 2026-01-12 | Soumodip Ghosh | Coding | 3- Completed | 18 | 4 | 2 | 3 | 4 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | T9.1 | Model lifecycle implementation | 2026-01-07 | 2026-01-12 | Soumodip Ghosh | Coding | 3- Completed | 11 | 1 | 1 | 3 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | T11.2 | Document workdone | 13-01-26 | 13-01-26 | Soumodip Ghosh | Documentation | 3- Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 8 BACKLOG
US-012 | T12.1 | Bug fixing and dashboard completion | 14-01-26 | 18-01-26 | Soumodip Ghosh | Coding | 3- Completed | 17 | 4 | 3 | 3 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T12.2 | Final testing | 22-01-26 | 25-01-26 | Soumodip Ghosh | Observing | 3- Completed | 13 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0
US-012 | T12.3 | Documentation | 26-01-26 | 28-01-26 | Soumodip Ghosh | Documentation | 3- Completed | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentors and team
S2 | Day 8 | Lack of clarity on models | Conducted a detailed discussion with mentors and team
S3 | Day 16 | Discussion on Ensemble | Conducted a detailed discussion with mentors and team
S4 | Day 24 | Discussion on required features | Conducted a detailed discussion with mentors and team
S5 | Day 29 | Discussion on backtesting logics | Conducted a detailed discussion with mentors and team
S6 | Day 38 | Gen AI shallow reply | Conducted a detailed discussion with mentors and team
S7 | Day 42 | Clarifying Model Life cycle | Conducted a detailed discussion with mentors and team
S8 | Day 56 | Testing and feedback | Conducted a discussion with mentors and team

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 26-11-2025 | 2025-02-12 | Soumodip Ghosh | Spend more time understanding fundamentals before implementation | Rushing into coding without clarity | Team discussions and reference reading | Allocated more time for learning and clarification in next sprint
2 | Sprint 2 | 2025-03-12 | 2025-09-12 | Soumodip Ghosh | Framing the model structure | Ignoring minor data issues initially | Collaborative problem-solving | Explore all models that I can implement
3 | Sprint 3 | 2025-10-12 | 16-12-2025 | Soumodip Ghosh | Ensembling outputs | Single model selection | Fine tuning | Collaboration
4 | Sprint 4 | 17-12-2025 | 23-12-2025 | Soumodip Ghosh | Making data pipeline | Working with static dataset | Train with updated dataset | Implement one click data insertion
5 | Sprint 5 | 24-12-2025 | 30-12-2025 | Soumodip Ghosh | Intricate with back testing | Relying only on accuracy | Consider the backtesting score | Backtesting score decide the precision
6 | Sprint 6 | 31-12-2025 | 2026-06-01 | Soumodip Ghosh | API and dashboard creation | File integration | Integrate with API | Create API for every module
7 | Sprint 7 | 2026-07-01 | 13-01-2026 | Soumodip Ghosh | API integration | Individual testing | Testing | Considering the prerequisite
8 | Sprint 8 | 14-01-2026 | 28-01-2026 | Soumodip Ghosh | Dashboard testing and Final PPT preparation, demo video recording, and documentation | Individual testing | Explicit Testing | Completed PPT, demo video, final documentation, and project submission